## 1230
Task List
Project Start Date: |  | 2017-04-25 | time axis 2017-04-24 to 2017-06-18
Display Week: |  | 1 | [6 empty] | 2017-04-24: Week 1; 2017-05-01: Week 2; 2017-05-08: Week 3; 2017-05-15: Week 4; 2017-05-22: Week 5; 2017-05-29: Week 6; 2017-06-05: Week 7; 2017-06-12: Week 8
[9 empty] | 2017-04-24 | [6 empty] | 2017-05-01 | [6 empty] | 2017-05-08 | [6 empty] | 2017-05-15 | [6 empty] | 2017-05-22 | [6 empty] | 2017-05-29 | [6 empty] | 2017-06-05 | [6 empty] | 2017-06-12
Task | Lead | Start | Estimate End | Status % Complete | Actual End | Duration | Days Delay | Remark | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
[.Net] |  | 2016-12-23 | 2017-01-13
3M | nick/gary | 2016-12-30 | 2016-12-30 | 100% | 2016-12-30 | 1 | 0 | remove old data
tmw | richard | 2016-12-26 | 2016-12-26 | 100% | 2016-12-26 | 1 | 0 | not assign a print shop to any order for IPP on the TMW
Invista | nick | 2016-12-29 | 2016-12-29 | 100% | 2016-12-29 | 1 | 0 | check Amy Zhang's account / password
jockey | james | 2017-01-04 | 2017-01-04 | 100% |  | 1 | 0 | check why “print selected lines” button is greyed out by default.
pvh | nick/gary | 2016-12-23 | 2017-01-05 | 100% |  | 14 | 0 | finished
pvh | nick/gary | 2017-01-06 | 2017-01-13 | 100% | 2017-01-11 | 8 | 0 | finished
[.Net] |  | 2017-01-03 | 2017-01-23
pvh | nick/gary | 2017-01-16 | 2017-01-20 | 100% | 2017-01-18 | 5 | 0 | finished
dana-co | joy | 2017-01-03 | 2017-01-13 | 100% | 2017-01-13 | 11 | 0 | finished
US polo ASSN | allen | 2017-01-09 | 2017-01-19 | 100% | 2017-01-13 | 11 | 0 | finished
US polo ASSN | allen | 2017-01-20 | 2017-01-20 | 100% | 2017-01-20 | 1 | 0 | modification
REAL METRO | james | 2017-01-09 | 2017-01-20 | 100% | 2017-01-19 | 12 | 0 | finished
BAB | joy | 2017-01-19 | 2017-01-19 | 100% | 2017-01-19 | 1 | 0 | MEXICO ADDRESS UPDATE
AMRG | nick/gary/james | 2017-01-19 | 2017-01-23 | 100% | 2017-01-23 | 5 | 0 | some changes to the catalog order
Hanes c9 | nick | 2017-01-19 | 2017-01-23 | 100% | 2017-01-23 | 5 | 0 | bugs: printing questions
Invista | nick/gary | 2017-01-20 | 2017-01-23 | 100% | 2017-01-23 | 4 | 0 | Problem with the Monthly Inventory report
[.Net] |  | 2017-02-02 | 2017-02-17
pvh | nick/gary | 2017-02-06 | 2017-02-17 | 100% | 2017-02-17 | 12 | 0 | new requirement
dana-co | joy | 2017-02-06 | 2017-02-13 | 100% | 2017-02-13 | 8 | 0 | some problem and deploy
US polo ASSN | allen | 2017-02-02 | 2017-02-09 | 100% | 2017-02-09 | 8 | 0 | some problem and deploy
tmw | richard | 2017-02-08 | 2017-02-13 | 100% | 2017-02-13 | 6 | 0 | New features
REAL METRO | james | 2017-02-07 | 2017-02-08 | 100% | 2017-02-08 | 2 | 0 | some bugs and new features
jockey | james | 2017-02-09 | 2017-02-09 | 100% | 2017-02-09 | 1 | 0 | No New styles in r-trac
express | joy | 2017-02-06 | 2017-02-17 | 100% | 2017-02-17 | 12 | 0 | new project
at home | nick/gary/james | 2017-02-03 | 2017-02-16 | 100% | 2017-02-16 | 14 | 0 | some changes
buckle | allen | 2017-02-03 | 2017-02-17 | 100% | 2017-02-17 | 15 | 0 | new project
AMRG | nick/gary/james | 2017-02-06 | 2017-02-17 | 100% | 2017-02-17 | 12 | 0 | Need urgent Minor Changes
3M | nick/gary | 2017-02-16 | 2017-02-17 | 100% | 2017-02-17 | 2 | 0 | in the test
[.Net] |  | 2017-02-20 | 2017-03-03
ah | james | 2017-02-20 | 2017-02-20 | 100% | 2017-02-17 | 1 | 0 | add new brand “RB” to the list of brands under the division screen
AMRG | nick/gary/james | 2017-02-20 | 2017-02-27 | 80% |  | 8 | 0 | 1。check and fix the bug:the field “Sale Price” is not being fed into the BTW files 2。apply the new show image and email logic 3。 Correct the payment term & adding the freight amount for Mark Shipped & shipbill country change $ keep one price for PO Item $ adding the list of production locations for catalog and po item setup & check if items is not available in shopping cart and apply the new logic & apply new change for POs with some catalog items 4 . upload the list of users
obey | james | 2017-02-23 | 2017-02-23 |  |  | 1 | 0 | check and fix the bug :fles not importing
tmw | richard | 2017-02-22 | 2017-02-27 | 80% |  | 6 | 0 | 1.changing the way to apply code 128 2. include the JobNo on the batched files and generate an email with the generated Zip file
dana-co | joy | 2017-02-23 | 2017-02-24 | 100% | 2017-02-24 | 2 | 0 | 1. add some search condition for In Plant Printing by Master Data and Job Setup List screen 2 . add ‘Overage’ drop down menu for Job Setup List screen 3 . new change: align the search condition after point 1 finished
buckle | allen | 2017-02-20 | 2017-02-24 | 80% |  | 5 | 0 | fix the bug after test and apply new import po item data logic
target | allen | 2017-02-22 | 2017-03-03 |  |  | 10 | 0 | new project just like hanesC9
Carrefour | joy/allen | 2017-02-21 | 2017-02-21 |  |  | 1 | 0 | reject :new project just want to convert the PDF to text and then mapping the report but hard to apply the format
M&S | richard | 2017-02-24 | 2017-02-24 | 100% | 2017-02-24 | 1 | 0 | providing Contract Numbers for some M&S PFL items.
at home | nick/gary/james | 2017-02-24 | 2017-02-27 | 100% | 2017-02-27 | 4 | 0 | some name change under Catalog item setup & Order Catalog items & Order by Purchase Order Number screen and Check why Round QTY function is not working
LF | winshow | 2017-02-24 | 2017-02-27 |  |  | 4 | 0 | 1. KOHL’s web interface changes request 2. changing the format of exporting PDF proof
Hanes c9 | nick | 2017-02-24 | 2017-02-24 | 100% | 2017-02-24 | 1 | 0 | bugs: printing questions
[.Net] |  | 2017-02-22 | 2017-03-07
mamiye | gary | 2017-02-27 | 2017-02-27 | 100% | 2017-02-27 | 1 | 0 | remove some Po data
tmw | richard | 2017-02-22 | 2017-02-27 | 100% | 2017-02-27 | 6 | 0 | 1.changing the way to apply code 128 2. include the JobNo on the batched files and generate an email with the generated Zip file
A&H | james | 2017-02-27 | 2017-02-27 | 100% | 2017-02-27 | 1 | 0 | Adding new brand “SA” under the brand section on the division screen
at home | nick/gary/james | 2017-02-28 | 2017-03-03 | 90% |  | 4 | 0 | 1. update the field names on the setup screen and the ordering screen 2. separate the Season and Collection into two separate fields under PO Item Setup 3. allow the user to assign multiple Ticket Types to the PO
express | joy | 2017-02-27 | 2017-03-01 | 100% | 2017-03-01 | 3 | 0 | 1 link the images to each item code setup in the catalog screen 2 add printint function to catalog item 3 include the French size to exported excel file
dana-co | joy | 2017-02-27 | 2017-03-01 | 100% | 2017-03-01 | 3 | 0 | 1. fixed the bugs: printing questions 2 . make the search in the text boxes under the place an order screen explicit and not wild search anymore 3 . disable notification emails for in plant printing orders
target | allen | 2017-02-22 | 2017-03-03 | 100% | 2017-03-02 | 10 | 0 | new project just like hanesC9
AMRG | nick/gary/james | 2017-02-28 | 2017-03-07 | 80% |  | 8 | 0 | 1。Modify last week's demand feedback 2。update the first status for a catalog PO to be “Pending Approval” instead of “NEW” 3。allow up to 20 sizes to be added in the ordering screen 4 check why the cancel button is not showing up on orders in “Pending Approval” status 5 generate the email for “Missing Image” only and only if the PO contains ticket Code AM-FWNPST04 6 limit the email for “Image received already exist” to be generated only one time 7 add Emily Braun emily.braun@r-pac.co to the email “Received AMRG files” 8 use “700” for the customer column in the billing report screen under reports tab
LF | winshow | 2017-02-28 | 2017-02-28 | 100% |  | 1 | 0 | fiixed the PDF proof & page issue
Life Time Brands | nick/gary | 2017-02-28 | 2017-02-28 | 100% | 2017-02-28 | 1 | 0 | check and fix the bug :missing some data in receive file
pvh | nick/gary | 2017-02-28 | 2017-03-01 | 100% | 2017-02-28 | 2 | 0 | 1. Replace the Text field “Wastage” in the PO detail page with a drop down (0%  15%) 2. In PO detail page, Use the same QTY in “Default QTY” field to be displayed in “UPC/EAN Order QTY”
buckle | allen | 2017-03-01 | 2017-03-03 | 80% |  | 3 | 0 | 1. One important Rule to implement: 2.. Update the logo on the site 3 . capture the “PO Start Date” and add it as a column in the grid in “Order by Purchase Order Number” screen 4. Generate a daily report to the vendor and to Buckle 10 days prior to the cancel date if the vendor has not released their order 5 . Change the overage drop down to have values from (-15%  15%) 6 . combined the columns “Customer PO” and “Client PO”
REAL METRO | james/joy | 2017-03-02 | 2017-03-03 |  |  | 2 | 0 | 1. add online approval for orders like Mamiye. 2. add a thumbnail image next to the item code drop down in the ordering screen 3 remove the column “WE” from the template and all of the screens 4. set the property of the excel file columns to TEXT so that values are imported properly when the template is uploaded
levy | joy | 2017-03-02 | 2017-03-03 | 100% | 2017-03-03 | 2 | 0 | add new format attached ‘STKRFID-007 (Elie Tahari Sticker & MSRP).btw’ to the Levy Group coding
[.Net] |  | 2017-02-28 | 2017-03-17
tmw | richard | 2017-03-09 | 2017-03-14 | 60% |  | 6 | 0 | build the last new big logic before roll into production
at home | nick/gary/james | 2017-03-09 | 2017-03-13 | 90% |  | 5 | 0 | 1. • Buttons (view, re-print) should be change the disabled way 2. • Add some fields to the grid in JobNo detail page 3. change the function for ticket type selected
express | joy | 2017-03-06 | 2017-03-07 | 100% |  | 2 | 0 | 1 update the size screen 2 change the way for Background_Image show 3 offer the list of all field names used in BTW
M&S | richard | 2017-03-07 | 2017-03-08 | 100% | 2017-03-08 | 2 | 0 | check the original file from M&S(Contract Number: 20136137) and see if we received duplicate entries for each item
buckle | allen | 2017-03-01 | 2017-03-07 | 100% |  | 7 | 0 | 1. One important Rule to implement: 2.. Update the logo on the site 3 . capture the “PO Start Date” and add it as a column in the grid in “Order by Purchase Order Number” screen 4. Generate a daily report to the vendor and to Buckle 10 days prior to the cancel date if the vendor has not released their order 5 . Change the overage drop down to have values from (-15%  15%) 6 . combined the columns “Customer PO” and “Client PO”
Letote | joy | 2017-03-08 | 2017-03-15 | 90% | 2017-03-15 | 8 | 0 | new project
Augusta National: | nick/gary/james | 2017-03-09 | 2017-03-17 | 10% |  | 9 | 0 | new project
target | allen/simon | 2017-03-09 | 2017-03-10 | 100% | 2017-03-10 | 2 | 0 | • Format drop down menu: include the ‘Item Code’ and not the ‘Format FileName & provide the data mapping name table & check the print problem
AMRG | nick/gary/james | 2017-02-28 | 2017-03-08 | 100% | 2017-03-08 | 9 | 0 | 1。Modify last week's demand feedback 2。update the first status for a catalog PO to be “Pending Approval” instead of “NEW” 3。allow up to 20 sizes to be added in the ordering screen 4 check why the cancel button is not showing up on orders in “Pending Approval” status 5 generate the email for “Missing Image” only and only if the PO contains ticket Code AM-FWNPST04 6 limit the email for “Image received already exist” to be generated only one time 7 add Emily Braun emily.braun@r-pac.co to the email “Received AMRG files” 8 use “700” for the customer column in the billing report screen under reports tab
REAL METRO | james/joy | 2017-03-08 | 2017-03-09 | 100% | 2017-03-09 | 2 | 0 | change and fixed the bug for last requirement
A&H | james | 2017-03-10 | 2017-03-10 | 100% | 2017-03-10 | 1 | 0 | add Rjimenez@swimusa.com to the rejection email we generate from r-trac.
[.Net] |  | 2017-03-08 | 2017-03-16
tmw | richard | 2017-03-09 | 2017-03-14 | 100% | 2017-03-14 | 6 | 0 | build the last new big logic before roll into production
buckle | allen/simon | 2017-03-14 | 2017-03-15 | 100% | 2017-03-15 | 2 | 0 | provide the data mapping name table & remove EL Salvador print shop and add “Hong Kong” print shop & check the btw mapping problem for Retail price field & add new field 'promotion price'
target | allen/simon | 2017-03-13 | 2017-03-13 | 100% | 2017-03-13 | 1 | 0 | provide the data mapping name table & check the qty print problem
REAL METRO | james/joy | 2017-03-14 | 2017-03-16 | 100% | 2017-03-16 | 3 | 0 | roles and permissions change & open office upload way
at home | nick/gary/james | 2017-03-13 | 2017-03-16 | 100% | 2017-03-16 | 4 | 0 | 1. Replace the warning info on the COO free text field 2. some change on Catalog items and Order by Purchase Order Section 3. change the function for ticket type selected just like M&S
AMRG | nick/gary/james | 2017-03-14 | 2017-03-14 | 100% | 2017-03-14 | 1 | 0 | check why DC orders are hanging when user click on confirm,
Letote | joy | 2017-03-08 | 2017-03-15 | 100% | 2017-03-14 | 8 | 0 | new project
pvh | nick/gary | 2017-03-14 | 2017-03-14 | 100% | 2017-03-14 | 1 | 0 | send the BTW field names & clear all of the test orders in the check order status screen
Robinson | joy/richard | 2017-03-14 | 2017-03-15 | 100% | 2017-03-15 | 2 | 0 | add four new sizes for item ' ROP-PL-EB-48504A' & update the data for item 'ROP-WT-EB-47005' & add new item 'ROP-WT-EB-47005 Gray'
mamiye | gary | 2017-03-15 | 2017-03-15 | 100% | 2017-03-15 | 1 | 0 | fix the export pdf files error
[.Net] |  | 2017-03-20 | 2017-03-31
tmw | richard | 2017-03-21 | 2017-03-23 | 100% | 2017-03-23 | 3 | 0 | build the last new big logic before roll into production
Augusta National: | nick/gary/james | 2017-03-20 | 2017-03-24 | 100% | 2017-03-24 | 5 | 0 | fixed some bug and change some thing after pull to test site
Hanes c9 | nick | 2017-03-20 | 2017-03-20 | 100% | 2017-03-20 | 1 | 0 | Remove RFId object from Non-RFID formats
A&H | james | 2017-03-21 | 2017-03-23 | 100% | 2017-03-23 | 3 | 0 | Add new brand
express | joy | 2017-03-20 | 2017-03-20 | 100% | 2017-03-20 | 1 | 0 | fix the bug on the PDF generated.
buckle | allen/simon | 2017-03-22 | 2017-03-23 | 100% | 2017-03-23 | 2 | 0 | deploy to production & install some fonts & add send email if the PO status is changed to “CHANGE”
jcpWebprint | ricahrd | 2017-03-20 | 2017-03-31 | 10% |  | 12 | 0 | new rfid project for Jcp to print
jockey | james | 2017-03-23 | 2017-03-24 | 100% | 2017-03-24 | 2 | 0 | fix the bug for printing time out
mamiye | gary | 2017-03-23 | 2017-03-25 | 80% |  | 3 | 0 | fix the bug for export pdf
AMRG | nick/gary/james | 2017-03-23 | 2017-03-23 | 100% | 2017-03-23 | 1 | 0 | add item code “FWNPST04” in addition to “AM- FWNPST04” when search incoming POs for missing images. Once done, run a report on all reports in the system with two item codes
pvh | nick/gary | 2017-03-23 | 2017-03-23 | 100% | 2017-03-23 | 1 | 0 | update the “Brand Division” screen with the new table & update the “Format Screen” to include a section with checkboxes for each GTINDepartment (obtained from the Brand Division screen)
[.Net] |  | 2017-03-27 | 2017-04-14
Letote | joy | 2017-03-27 | 2017-03-28 | 100% | 2017-03-28 | 2 | 0 | check why the re-print is not getting new EPC numbers $ deploy this project to 192.168.70.85 for production
Life Time Brands | nick/gary | 2017-03-28 | 2017-03-28 | 100% | 2017-03-28 | 1 | 0 | add some users & adjust the import logic
mamiye | gary | 2017-03-28 | 2017-03-31 | 100% | 2017-03-31 | 4 | 0 | fix the bug for export pdf & Remove PO 1046875
macy's | james | 2017-03-28 | 2017-03-28 | 100% | 2017-03-28 | 1 | 0 | add some users
Uniqlo | allen/joy | 2017-03-27 | 2017-04-14 | 20% |  | 19 | 0 | new project
express | joy | 2017-03-29 | 2017-03-31 | 100% | 2017-03-31 | 3 | 0 | change the way to export layout & make the image clear
AMRG | nick/gary/james | 2017-03-31 | 2017-03-31 | 100% | 2017-03-31 | 1 | 0 | run a report on all reports in the system with two item codes( “FWNPST04” & “AM- FWNPST04”) and find out what images are we missing
at home | nick/gary/james | 2017-03-29 | 2017-03-30 | 100% | 2017-03-30 | 2 | 0 | 1. Please hide (New Jersey, India) from the production locations drop down in “Order by purchase order number” screen. 2.chekc why the Season and collection drop downs are not appearing on the ordering screen when the flag is set to YES.
buckle | allen/simon | 2017-03-29 | 2017-03-30 | 100% | 2017-03-30 | 2 | 0 | check why the test Po is not import to production site & adjust the PO Change notification email include the email address of any user account with matching vendor ID on the notification email & add some people to Hong Kong Print shop and andcustomer email.
jcpWebprint | james | 2017-03-30 | 2017-04-07 | 20% |  | 9 | 0 | new rfid project for Jcp to print
dana-co | joy | 2017-03-28 | 2017-03-29 | 100% | 2017-03-29 | 2 | 0 | capture the new Column Pick Number and including to the project
jockey | james | 2017-03-30 | 2017-03-30 | 90% |  | 1 | 0 | urgently: check the print problem
Invista | nick/gary | 2017-03-30 | 2017-03-30 | 100% | 2017-03-30 | 1 | 0 | check why the order is not import
[.Net] |  | 2017-03-27 | 2017-04-14
tmw | richard | 2017-04-06 | 2017-04-07 | 100% | 2017-04-07 | 2 | 0 | roll into production
AMRG | nick/gary/james | 2017-04-03 | 2017-04-05 | 100% | 2017-04-05 | 3 | 0 | check if all of the images associated with Pos & add user email & fix the round up qty issue
express | joy | 2017-04-05 | 2017-04-06 | 100% | 2017-04-06 | 2 | 0 | roll into production & restart the computer
levy | joy | 2017-04-06 | 2017-04-06 | 100% | 2017-04-06 | 1 | 0 | fix the bug of receiving email
Uniqlo | allen/joy | 2017-03-27 | 2017-04-14 | 80% |  | 19 | 0 | new project
buckle | allen/simon | 2017-04-05 | 2017-04-07 | 100% | 2017-04-07 | 3 | 0 | use “800” for the customer column in billing report screen under Reports tab & add the attached list of Buckle users & check the bug of receiving email & add some user email
REAL METRO | james/joy | 2017-04-06 | 2017-04-11 | 30% |  | 6 | 0 | add some big modifications
at home | nick/gary/james | 2017-04-07 | 2017-04-07 | 100% | 2017-04-07 | 1 | 0 | 1. Please confirm notification email is turned on. 2. Add some email addresses.
jcpWebprint | james | 2017-03-30 | 2017-04-07 | 100% | 2017-04-07 | 9 | 0 | new rfid project for Jcp to print
bab | joy | 2017-04-07 | 2017-04-07 | 100% | 2017-04-07 | 1 | 0 | check why no email sent
jockey | james | 2017-03-30 | 2017-04-06 | 100% | 2017-04-06 | 8 | 0 | roll into 70.62 and waiting observation
[.Net] |  | 2017-03-27 | 2017-04-14
tmw | richard | 2017-04-10 | 2017-04-13 | 100% | 2017-04-13 | 4 | 0 | Orders going to “China” production location change to “New” status & once an order is placed the country is saved into the address book for the user & make sure the delete user can not login in & enable “Batch Order” for catalog items & add some fields in “Summary Order” file & JobNo detail page under the Ship to section.
Uniqlo | allen/joy | 2017-03-27 | 2017-04-14 | 80% |  | 19 | 0 | new project:delay
AMRG | nick/gary/james | 2017-04-10 | 2017-04-14 | 100% | 2017-04-14 | 5 | 0 | setup a rule to explode this item code AMRGSOMSTK if received from AMRG file to M-STKR & AMRG-SO & check why cannot export layout & some change in master and main
mamiye | gary | 2017-04-11 | 2017-04-14 | 100% | 2017-04-14 | 4 | 0 | check the Image Issue &check why Import program is not working
target | allen/simon | 2017-04-11 | 2017-04-13 | 100% | 2017-04-13 | 3 | 0 | check why can’t export the PDF layout & update the PDF proof format
Augusta National: | nick/gary/james | 2017-04-12 | 2017-04-14 | 100% | 2017-04-14 | 3 | 0 | use a specific encoding schema for two types of barcodes
express | joy | 2017-04-13 | 2017-04-14 | 100% | 2017-04-14 | 2 | 0 | change some thing in Check Order Status & Order Catalog Items
buckle | allen/simon | 2017-04-11 | 2017-04-14 | 100% | 2017-04-14 | 4 | 0 | add ‘United States’ to Production Location & add some emali to the order notification emails &add “cancel date” column to the exported excel order file
at home | nick/gary/james | 2017-04-10 | 2017-04-10 | 100% | 2017-04-10 | 1 | 0 | check why the cancel button is not showing up for Athome vendor role even though the permission is assigned to them. & ensure print shop personal are copied on the customer email as well.
US polo ASSN | allen/Sakho | 2017-04-11 | 2017-04-13 | 100% | 2017-04-13 | 3 | 0 | add logic to US Polo ASSN to assign production locations to each item (similar to AMRG site)
M&S | richard | 2017-04-14 | 2017-04-14 | 100% | 2017-04-14 | 1 | 0 | check why the third composition did not get captured in r-trac even though it exist in the PLM file
[.Net] |  | 2017-04-17 | 2017-04-24
M&S | richard/garden | 2017-04-18 | 2017-04-21 | 100% | 2017-04-21 | 4 | 0 | check why get blank excel file.
mamiye | gary | 2017-04-17 | 2017-04-21 | 100% | 2017-04-21 | 5 | 0 | check why open the files error& edit and upload the attached images and formats on Mamiye r-trac, the new images are not reflected on r-trac
robinson | joy | 2017-04-17 | 2017-04-21 | 100% | 2017-04-21 | 5 | 0 | update the notification email and remove Leaf Duan & CL.Lam get the additional quantity breaks entered on the ROP r-trac site
Invista | nick/ | 2017-04-18 | 2017-04-18 | 100% | 2017-04-18 | 1 | 0 | mark some orders (with status partially shipped) as cancelled
Augusta National: | nick/gary/james | 2017-04-18 | 2017-04-21 | 100% | 2017-04-21 | 4 | 0 | some requirements about print & images issue & remove Torsten email from Augusta Testing site
Life Time Brands | nick/gary | 2017-04-18 | 2017-04-18 | 100% | 2017-04-18 | 1 | 0 | check and fix the printing issue reported belo
Uniqlo | allen/joy | 2017-04-18 | 2017-04-20 | 100% | 2017-04-20 | 3 | 0 | add the Type drop down for RFID and Non-RFID in the New screen under PO item setup. & some bug and some new change after first test
AMRG | nick/gary/james | 2017-04-20 | 2017-04-21 | 100% | 2017-04-21 | 2 | 0 | check why Edit and Cancel buttons not showing to AMRG vendor role despite that the permission for each is added to this role & check why the list of print shops under the billing report screen only shows All or HK.
at home | nick/gary/james | 2017-04-18 | 2017-04-21 | 80% | 2017-04-21 | 4 | 0 | allow the user to edit the shipping info by enabling the “Mark Shipped” button if an order is already marked shipped. & check the print bug
buckle | simon/sk | 2017-04-17 | 2017-04-21 | 100% | 2017-04-21 | 5 | 0 | some change about import logic
jcpWebprint | james | 2017-04-17 | 2017-04-24 | 90% | 2017-04-24 | 8 | 0 | new rfid project for Jcp to print
tmw | richard | 2017-04-17 | 2017-04-17 | 100% | 2017-04-17 | 1 | 0 | add some fields in export order file
US polo ASSN | Sakho | 2017-04-17 | 2017-04-21 | 100% | 2017-04-21 | 5 | 0 | check why the production location function for item code is missing
[.Net] |  | 2017-04-24 | 2017-04-28
M&S | richard/garden | 2017-04-24 | 2017-04-28 | 100% | 2017-04-28 | 5 | 0 | fix the import project and fix the error data
Augusta National: | nick/gary/james | 2017-04-24 | 2017-04-28 | 100% | 2017-04-28 | 5 | 0 | check why the Cancel, Export PDF buttons are not showing up for the “Augusta Vendor” role & finish customer's changes ASAP &explode the SKU to 2 or 3 SKUs with the same data based on the ticket codes received
robinson | joy | 2017-04-24 | 2017-04-24 | 100% | 2017-04-24 | 1 | 0 | add some new item code
Uniqlo | allen/joy | 2017-04-25 | 2017-04-28 | 100% | 2017-04-28 | 4 | 0 | some big change after feedback
3M | nick/gary | 2017-04-25 | 2017-04-28 | 100% | 2017-04-28 | 4 | 0 | some big change
buckle | allen/simon | 2017-04-25 | 2017-04-28 | 100% | 2017-04-28 | 4 | 0 | fix the email bug & change the print shop name “United States” on Buckle r-trac to “USA” and ensure all screens are updated. & fix a problem in the import program
target | allen/simon | 2017-04-26 | 2017-04-26 | 100% | 2017-04-26 | 1 | 0 | don’t change the format name to date and keep it as it is
macy's | james | 2017-04-27 | 2017-04-28 | 100% | 2017-04-28 | 2 | 0 | check why not imported anything since 12/08/2016
A&H | james | 2017-04-27 | 2017-04-27 | 100% | 2017-04-27 | 1 | 0 | fix the email bug form customer
obey | james | 2017-04-27 | 2017-04-27 | 100% | 2017-04-27 | 1 | 0 | many orders created with one user Acmefashions on Obey r-trac site however do not see the user on the access tab
at home | nick/gary/james | 2017-04-27 | 2017-04-28 | 100% | 2017-04-28 | 2 | 0 | ensure print shop AEs are copied on both emails generated when an order is cancelled & expected a general separator, please help to check if it’s workable
dana-co | joy | 2017-04-28 | 2017-04-28 | 100% | 2017-04-28 | 1 | 0 | check the upc data problem
tmw | richard | 2017-04-28 | 2017-04-28 | 100% | 2017-04-28 | 1 | 0 | update the status of job no 'TMW201704280030218' from Cancelled to INPROCESS
[.Net] |  | 2017-05-02 | 2017-05-05
tmw | richard | 2017-05-02 | 2017-05-02 | 100% | 2017-05-02 | 1 | 0 | remove India print shop from TMW r-trac website.
jcpWebprint | james | 2017-05-02 | 2017-05-02 | 100% | 2017-05-02 | 1 | 0 | create test site http://jcprfidtest.r-pac.com.hk on 192.168.42.3.
aerosole | joy | 2017-05-02 | 2017-05-02 | 100% | 2017-05-02 | 1 | 0 | update notification email.
AMRG | nick/gary/james | 2017-05-02 | 2017-05-02 | 100% | 2017-05-02 | 1 | 0 | adjust the btw file
at home | nick/gary/james | 2017-05-02 | 2017-05-02 | 100% | 2017-05-02 | 1 | 0 | adjust the btw file
buckle | allen/sk | 2017-05-02 | 2017-05-02 | 100% | 2017-05-02 | 1 | 0 | change the information for help on r-trac for Buckle
dana-co | joy | 2017-05-04 | 2017-05-05 | 100% | 2017-05-05 | 2 | 0 | check the Pick Number. data problem
M&S | richard/garden | 2017-05-03 | 2017-05-03 | 100% | 2017-05-03 | 1 | 0 | check some job data problem
pvh | nick/gary | 2017-05-02 | 2017-05-03 | 100% | 2017-05-03 | 2 | 0 | add color bar
US polo ASSN | Sakho | 2017-05-03 | 2017-05-04 | 100% | 2017-05-04 | 2 | 0 | change the way to place order
Uniqlo | allen/joy | 2017-05-02 | 2017-05-05 | 100% | 2017-05-05 | 4 | 0 | some big change after feedback
Letote | joy | 2017-05-04 | 2017-05-05 | 100% | 2017-05-05 | 2 | 0 | add new requrement of Customer logic
Hanes c9 | joy | 2017-05-04 | 2017-05-04 | 100% | 2017-05-04 | 1 | 0 | check and fix the pdf issue
[.Net] |  | 2016-12-07 | 2017-06-07
uniqlo | allen/joy | 2017-05-09 | 2017-05-11 | 100% | 2017-05-11 | 3 | 0 | phase6
TMW | richard | 2017-05-10 | 2017-05-11 | 100% | 2017-05-11 | 2 | 0 | check code128 issues and reform A4 format
PVH | nick/gary | 2017-05-11 | 2017-05-11 | 100% | 2017-05-11 | 1 | 0 | Add color bar/creating color bar
Justice | [7 empty] | new project
JCP | james | 2017-05-08 | 2017-05-12 | 100% | 2017-05-12 | 5 | 0 | New Major updates about order data
Buckle | Sakho | 2017-05-08 | 2017-05-11 | 100% | 2017-05-11 | 4 | 0 | split email rules on Cancel order report
Hanes c9 | joy | 2017-05-11 | 2017-05-12 | 100% | 2017-05-12 | 2 | 0 | modification
BAB | joy | 2017-05-08 | 2017-05-08 | 100% | 2017-05-08 | 1 | 0 | plush hangtag for Turkey
[.Net] |  | 2017-05-15 | 2017-05-26
uniqlo | allen/joy | 2017-05-15 | 2017-05-17 | 100% | 2017-05-17 | 3 | 0 | fixed some bugs for phase6
TMW | richard | 2017-05-15 | 2017-05-16 | 100% | 2017-05-16 | 2 | 0 | change the way to show barcode & add some content to separator btw file & adjust the packing list file format & adjust the batch function
SEARS | joy | 2017-05-15 | 2017-05-19 | 100% | 2017-05-19 | 5 | 0 | new project
Buckle | Sakho | 2017-05-15 | 2017-05-15 | 100% | 2017-05-15 | 1 | 0 | change the encoding code for billing report file & remove diane.applegate@buckle.com from the list of recipients of cancel order report
robinson | joy | 2017-05-15 | 2017-05-15 | 100% | 2017-05-15 | 1 | 0 | update some item code info
AMRG | gary/james | 2017-05-16 | 2017-05-16 | 100% | 2017-05-16 | 1 | 0 | fixed the bug of qty issue
Letote | joy/sakho | 2017-05-16 | 2017-05-16 | 100% | 2017-05-16 | 1 | 0 | split the job into a multiple lines of 2000 each
Hanes c9 | joy/james | 2017-05-17 | 2017-05-18 | 100% | 2017-05-18 | 2 | 0 | Remove RFId object from Non-RFID formats & check the print issue
PVH | gary | 2017-05-17 | 2017-05-18 | 100% | 2017-05-18 | 2 | 0 | offer original customer files
Augusta National: | sakho | 2017-05-17 | 2017-05-17 | 100% | 2017-05-17 | 1 | 0 | test order purge
REAL METRO | james/joy | 2017-05-18 | 2017-05-19 | 100% | 2017-05-19 | 2 | 0 | fixed the bug of sending email to VENDOR after upload PDF for proofing by admin
3M | gary/sakho | 2017-05-18 | 2017-05-18 | 100% | 2017-05-18 | 1 | 0 | fix the bug for item in Item Master screen
at home | gary/james | 2017-05-17 | 2017-05-18 | 100% | 2017-05-18 | 2 | 0 | fix the bug for PO ordered status
Clarks | Sakho | 2017-05-19 | 2017-05-26 | 10% |  | 8 | 0 | new project
| richard | 2017-05-18 | 2017-05-18 | 100% | 2017-05-18 | 1 | 0 | install related software on 70.87 & 70.88 server
[.Net] |  | 2017-05-19 | 2017-06-07
TMW | richard | 2017-05-24 | 2017-05-25 | 100% | 2017-05-25 | 2 | 0 | show the image upload to each item to the PDF proof and check the overlap issue stated by Terence
website move work | richard | 2017-05-24 | 2017-05-26 | 100% | 2017-05-26 | 3 | 0 | move some website from 70.82 to 70.87 & 70.88
BAB | joy | 2017-05-23 | 2017-05-23 | 100% | 2017-05-23 | 1 | 0 | plush hangtag for Turkey
Hanes c9 | joy/james | 2017-05-23 | 2017-05-23 | 100% | 2017-05-23 | 1 | 0 | update two formats on production site as well by removing RFID object and ensuring the QTY is mapped correctly
AMRG | gary/james | 2017-05-23 | 2017-05-23 | 100% | 2017-05-23 | 1 | 0 | Add MOQ\Order
Augusta National: | sakho | 2017-05-24 | 2017-05-24 | 100% | 2017-05-24 | 1 | 0 | reset the PO Ordered status for below POs to “NO”( ANI10784, ANI9131 & ANI5645.) and remove some test data
SEARS | joy | 2017-05-24 | 2017-05-26 | 100% | 2017-05-26 | 3 | 0 | new project with some big change
GALERIES LAFAYETTE | allen | 2017-05-24 | 2017-06-07 | 10% |  | 15 | 0 | new project
Clarks | Sakho | 2017-05-19 | 2017-05-26 | 100% | 2017-05-26 | 8 | 0 | new project
Life Time Brands | sakho/gary | 2017-05-26 | 2017-05-26 | 100% | 2017-05-26 | 1 | 0 | check why can’t get a confirmation Screen to save the job
uniqlo | allen/joy | 2017-05-25 | 2017-06-01 | 10% |  | 8 | 0 | some big new requiement
[.Net] |  | 2017-05-24 | 2017-06-07
TMW | richard | 2017-05-31 | 2017-06-01 | 100% | 2017-06-01 | 2 | 0 | change the qty column format to number instead of text In the batch order file & empty the data from the “Compare At” column if the data = 0.00 & Remove “ IN” from the “Full Size” field if the data before is not numeric & Remove “ CM” from the “Full Converted Size” field if the data before is not numeric
website move work | richard | 2017-05-31 | 2017-06-01 | 100% | 2017-06-01 | 2 | 0 | check the status and issue of all website in 70.87 & 70.88
BAB | joy | 2017-05-31 | 2017-05-31 | 100% | 2017-05-31 | 1 | 0 | check why No layout generated for BAB system
PVH | gary | 2017-05-31 | 2017-05-31 | 100% | 2017-05-31 | 1 | 0 | offer original customer files
AMRG | gary/james | 2017-05-31 | 2017-05-31 | 100% | 2017-05-31 | 1 | 0 | add Export button to all of the screens under Master.
SEARS | joy | 2017-05-31 | 2017-06-02 | 100% | 2017-06-02 | 3 | 0 | some big change after feedback
GALERIES LAFAYETTE | allen/sakho | 2017-05-24 | 2017-06-07 | 10% |  | 15 | 0 | new project need to finish in two week
Clarks | Sakho | 2017-06-01 | 2017-06-02 | 100% | 2017-06-02 | 2 | 0 | new project : some change after feedback
Augusta National: | sakho/gary | 2017-06-02 | 2017-06-02 | 100% | 2017-06-02 | 1 | 0 | check the problems with updating Augusta POs
servers mapping report | richard | 2017-06-01 | 2017-06-01 | 100% | 2017-06-01 | 1 | 0 | offer a report for drive mapping with r-trac machines(70.x & 42.X)
[Python] |  | 2016-12-07 | 2016-12-30
QVC | Garden | 2016-12-07 | 2016-12-20 | 100% | 2016-12-20 | 14 | 0 | PDF proof for COO label: wait for confirm
rfid-iimport | SK | 2016-12-23 | 2016-12-28 | 100% | 2016-12-28 | 6 | 0 | PVH
Tribal | Kevin/Eric | 2016-12-22 | 2016-12-29 | 100% | 2016-12-30 | 8 | 1days | Report update and daily maintenance.
ORC | Garden/Eric | 2016-12-28 | 2016-12-30 | 100% | 2016-12-30 | 3 | 0 | Update 2 new Label.
[Python] |  | 2017-01-03 | 2017-01-16
GAP | Kevin | 2017-01-05 | 2017-01-05 | 100% | 2017-01-05 | 1 | 0 | Update data
Dana-import | SK | 2017-01-03 | 2017-01-11 | 100% | 2017-01-11 | 9 | 0 | dana-co,新项目，完成初步数据导入，测试中
PVH-import | SK | 2017-01-04 | 2017-01-13 | 100% | 2017-01-12 | 10 | 0 | PVH数据修改
ORC | Garden/Eric | 2017-01-03 | 2017-01-03 | 100% | 2017-01-03 | 1 | 0 | Update HK LABEL
AEO | Eric | 2017-01-04 | 2017-01-16 | 100% | 2017-01-16 | 13 | 0 | Update AEO DATA 和 AEO CARE 洗水逻辑调整
[Python] |  | 2017-01-11 | 2017-01-12
ORC | Garden | 2017-01-11 | 2017-01-11 | 100% | 2017-01-11 | 1 | 0 | FIX BUG
GAP | Eric | 2017-01-11 | 2017-01-11 | 100% | 2017-01-11 | 1 | 0 | UPDATE GAP LIVE “pirce ticket”
AEO | Eric | 2017-01-12 | 2017-01-12 | 100% | 2017-01-12 | 1 | 0 | 导出数据报表
[Python] |  | 2017-01-17 | 2017-02-06
Tribal | Eric | 2017-01-17 | 2017-01-19 | 100% | 2017-01-19 | 3 | 0 | 更新成员权限
Quotation | Eric | 2017-01-17 | 2017-01-19 | 100% | 2017-01-19 | 3 | 0 | FIX BUG
ORC | Garden | 2017-01-17 | 2017-01-20 | 100% | 2017-01-20 | 4 | 0 | FIX BUG
Tribal | Kevin | 2017-01-20 | 2017-02-06 | 10% |  | 18 | 0 | 增加两行统计数据
[Python] |  | 2017-02-06 | 2017-03-03
ORC | Eric/Garden | 2017-02-06 | 2017-02-08 | 100% | 2017-02-08 | 3 | 0 | FIX BUG
AEO | Eric | 2017-02-06 | 2017-02-10 | 100% | 2017-02-10 | 5 | 0 | 修改the Brand is Aerie and the division is International 的业务逻辑
HBC | Garden/Kevin | 2017-02-13 | 2017-03-03 | 100% | 2017-03-03 | 19 | 0 | 完成
Tribal | Eric | 2017-02-13 | 2017-03-03 | 10% | 2017-03-03 | 19 | 0 | 新需求，加多一个下单类型。
Tribal | Kevin | 2017-02-13 |  |  |  |  | 0 | 修改报表，暂无时间修改。
ORC | Garden | 2017-02-14 | 2017-02-15 | 100% | 2017-02-15 | 2 | 0 | FIX BUG
Tribal | Eric | 2017-02-15 |  |  |  |  | 0 | 调整Tribal 用户，剔除无效用户，增加有效用户
QVC | Garden | 2017-02-14 | 2017-02-15 | 100% | 2017-02-15 | 2 | 0 | Add one more column to PO status view.
rfid-import | Garden | 2017-02-14 | 2017-02-16 | 100% | 2017-02-16 | 3 | 0 | FIX BUG
buckle | SK | 2017-02-10 | 2017-02-17 | 100% | 2017-02-16 | 8 | 0 | 新项目，完成数据处理，测试中
GAP | Kevin | 2017-02-10 | 2017-02-17 | 100% | 2017-02-16 | 8 | 0 | FIX BUG
[Python] |  | 2017-02-22 | 2017-02-24
buckle | SK | 2017-02-22 | 2017-02-24 | 100% | 2017-02-16 | 3 | 0 | add tag T
ORC | Garden | 2017-02-22 | 2017-02-22 | 100% | 2017-02-22 | 1 | 0 | Modify size BUG
AEO | Eric | 2017-02-23 | 2017-02-23 | 100% | 2017-02-23 | 1 | 0 | Modify Excel NEW REQUEST BUG
Tribal | Eric | 2017-02-23 | 2017-02-23 | 100% | 2017-02-23 | 1 | 0 | ADD NEW USER
[Python] |  | 2017-02-27 | 2017-03-03
buckle | SK | 2017-03-01 | 2017-03-03 | 100% | 2017-03-03 | 3 | 0 | add po_ordered status "CHANGE",waiting for testing
label-system | Garden/Eric | 2017-02-27 | 2017-02-27 | 100% | 2017-02-27 | 1 | 0 | fix bug
QVC | Garden | 2017-02-27 | 2017-02-27 | 100% | 2017-02-27 | 1 | 0 | update layout to fix one bug
import-macys | Garden | 2017-02-28 | 2017-02-28 | 100% | 2017-02-28 | 1 | 0 | reimport data
AEO | Eric | 2017-02-27 | 2017-02-28 | 100% | 2017-02-28 | 2 | 0 | AEO EXCEL UPDATE
Cabelas | Eric | 2017-02-27 | 2017-02-27 | 100% | 2017-02-27 | 1 | 0 | Memory error,FIX
AEO | Eric | 2017-03-02 | 2017-03-02 | 100% | 2017-03-02 | 1 | 0 | AEO EXCEL UPDATE
Tribal | Garden | 2017-02-27 | 2017-03-03 | 80% | 2017-03-03 | 5 | 0 | New Require 3D Printing Coding
[Python] |  | 2017-03-03 | 2017-03-07
QVC | Garden | 2017-03-07 | 2017-03-07 | 100% | 2017-03-07 | 1 | 0 | update item code list
import-amrg | Garden | 2017-03-03 | 2017-03-07 | 100% | 2017-03-07 | 5 | 0 | add images check email notify
buckle | SK | 2017-03-06 | 2017-03-08 | 100% | 2017-03-03 | 3 | 0 | change the method of delete orders of the cancel_date one day pass current date
tribal | Kevin | 2017-03-06 | 2017-03-10 | 100% | 03/16/17 | 5 |  | add the new column and fill the data to the excel report
tribal | Garden | 2017-03-09 | 2017-03-09 | 100% | 2017-03-09 | 1 | 0 | JOB interface adjustment
tribal | Eric | 2017-03-06 | 2017-03-06 | 100% | 2017-03-06 | 1 |  | ADD NEW USE AND NEW TEAM
C&A | Eric | 2017-03-07 | 2017-03-07 | 100% | 2017-03-07 | 1 |  | UP AEO TEST LOGO TO C&A LOGO
quotation | Eric | 2017-03-09 | 2017-03-09 | 100% | 2017-03-09 | 1 |  | Failed to log in.
[Python] |  | 2017-03-13 | 2017-03-16
buckle | SK | 2017-03-15 | 2017-03-16 | 100% | 2017-03-16 | 2 | 0 | add column promotion_price
augusta | SK | 2017-03-13 | 2017-03-15 | 100% | 2017-03-15 | 3 | 0 | new
rfid-import | Garden | 2017-03-13 | 2017-03-15 | 100% | 2017-03-15 | 3 | 0 | update
AEO | Eric | 2017-03-15 | 2017-03-17 | 100% | 2017-03-17 | 3 | 0 | greek coo excel update
quotation | Eric | 2017-03-15 | 2017-03-15 | 100% | 2017-03-15 | 1 | 0 | download word BUG FIX
Gap | Eric | 2017-03-10 | 2017-03-17 | 100% | 2017-03-17 | 8 | 0 | GAP EXCEL UPDATE
[Python] |  | 2017-03-20 | 2017-03-29
buckle | SK | 2017-03-22 | 2017-03-23 | 100% | 2017-03-23 | 2 | 0 | add mail when status of po_ordered change
Tribal | Kevin | 2017-03-20 | 2017-03-29 | 80% |  | 10 |  | remove the row of excel,wait to confirm, and alert email contact list
ImportMonitor | Garden | 2017-03-20 | 2017-03-24 | 70% | 2017-03-24 | 5 |  | import status monitor
AEO | Eric | 2017-03-20 | 2017-03-22 | 100% | 2017-03-22 | 3 | 0 | AEO Gcard UPDATE
[Python] |  | 2017-03-27 | 2017-03-31
rfid-import | Garden | 2017-03-27 | 2017-03-31 | 100% | 2017-03-31 | 5 | 0 | Minor fix or update.
QVC | Garden | 2017-03-27 | 2017-03-31 | 100% | 2017-03-31 | 5 | 0 | Minor fix or update.
Systemstatus | Garden | 2017-03-27 | 2017-03-31 | 100% | 2017-03-31 | 5 | 0 | Minor fix or update.
GAP | Kevin | 2017-03-29 | 2017-03-31 | 100% | 2017-03-31 | 3 | 0 | backup the data from gap test to gap live, update the all code to gap live,update the size data
buckle | SK | 2017-03-27 | 2017-03-29 | 100% | 2017-03-29 | 3 | 0 | add email address for status of change mail, modify the way of get new files
danaco | SK | 2017-03-29 | 2017-03-30 | 100% | 2017-03-30 | 2 | 0 | modify parse.py
[Python] |  | 2017-03-31 | 2017-04-07
rfid-import | Garden | 2017-04-03 | 2017-04-07 | 100% | 2017-04-07 | 5 | 0 | Minor fix or update.
khols | Kevin | 2017-03-31 | 2017-04-05 | 100% |  | 6 |  | add the function of upload format file and fix the bug
Gap | Kevin | 2017-04-03 | 2017-04-06 | 100% |  | 4 |  | fix the bug
danaco | SK | 2017-04-03 | 2017-04-03 | 100% | 2017-04-03 | 1 | 0 | change the frequence of parse file
[Python] |  | 2017-04-10 | 2017-04-14
rfid-import | Garden | 2017-04-10 | 2017-04-14 | 100% | 2017-04-14 | 5 | 0 | Minor fix or update.
QVC | Garden | 2017-04-10 | 2017-04-14 | 100% | 2017-04-14 | 5 | 0 | Minor fix or update.
parse_xls | SK | 2017-04-11 | 2017-04-13 | 100% | 2017-04-13 | 3 | 0 | parse the customer xls file to a sheet
[Python] |  | 2017-04-10 | 2017-04-21
Tribal | Kevin\Eric | 2017-04-10 | 2017-04-21 | 100% | 2017-04-13 | 12 | 0 | User List、Job Report
Aeo | Eric | 2017-04-13 | 2017-04-13 | 100% | 2017-04-13 | 1 | 0 | Aeo BUG Fix，MX MISS DES
HBC | Kevin/Jerry | 2017-04-08 | 2017-04-13 | 100% | 2017-04-13 | 6 | 0 | revision the logic about the instruction care, fix the layout space if so much data
[Python] |  | 2017-04-17 | 2017-04-21
buckle | SK | 2017-04-17 | 2017-04-21 | 100% | 2017-04-21 | 5 | 0 | fixed some bug
augusta | SK | 2017-04-17 | 2017-04-18 | 100% | 2017-04-18 | 2 | 0 | now can import file that may not use 'utf-8'
rfid-import | Garden | 2017-04-17 | 2017-04-21 | 100% | 2017-04-14 | 5 | 0 | Minor fix or update.
Kohls | Kevin | 2017-04-17 | 2017-04-18 | 100% | 2017-04-14 | 2 | 0 | upload the format file in system
Tribal | Kevin\Eric | 2017-04-10 | 2017-04-21 | 100% | 2017-04-14 | 12 | 0 | update order
Cabelas | Eric | 2017-04-18 | 2017-04-18 | 100% | 2017-04-18 | 1 | 0 | Import EDI File
AEO | Eric | 2017-04-19 | 2017-04-19 | 100% | 2017-04-19 | 1 | 0 | fix email BUG
augusta | SK | 2017-04-26 | 2017-04-27 | 100% | 2017-04-27 | 2 | 0 | add two col, add mail attach file
Gap | Kevin | 2017-04-12 | 2017-04-27 | 100% |  |  | 0 | create a function to download the excel of list information
[Python] |  | 2017-04-24 | 2017-04-28
rfid-import | Garden | 2017-04-24 | 2017-04-28 | 100% | 2017-04-14 | 5 | 0 | fix MS bug; fix maycs bug;
AEO | Garden | 2017-04-24 | 2017-04-28 | 100% | 2017-04-14 | 5 | 0 | Devlope new requirements.
rlabel | Garden | 2017-04-24 | 2017-04-28 | 100% | 2017-04-14 | 5 | 0 | Minor update.
Tribal | Eric | 2017-04-24 | 2017-04-28 | 100% | 2017-04-14 | 5 | 0 | update user list B、F team
[Python] |  | 2017-05-01 | 2017-05-05
AEO | Garden | 2017-05-01 | 2017-05-05 | 100% | 2017-05-05 | 5 | 0 | Devlope new requirements.
danaco | SK | 2017-05-03 | 2017-05-05 | 100% | 2017-05-05 | 3 | 0 | for file pick export.csv, not parsed now
augusta | SK | 2017-05-02 | 2017-05-03 | 100% | 2017-05-05 | 2 | 2days | solve some bugs
Tribal | Eric | 2017-05-02 | 2017-05-05 | 100% | 2017-05-05 | 4 | 0 | update user list B team
Aeo | Eric | 2017-05-05 | 2017-05-10 | 100% | 2017-05-05 | 6 | 0 | Fix Gcard BUG
Cabelas | Eric | 2017-05-05 | 2017-05-05 | 100% | 2017-05-05 | 1 | 0 | Import Edi file，check Data
Tribal | Kevin | 2017-04-26 | 2017-05-10 | 90% |  | 15 | 0 | Update the team report
excel parse | SK | 2017-05-08 | 2017-05-10 | 100% | 2017-05-10 | 3 | 0 | complete
Tribal | eric | 2017-05-16 | 2017-05-18 | 100% | 2017-05-18 |  |  | FIX BUG.DB memory overflow.
AEO | Eric/Garden | 2017-05-16 | 2017-05-18 | 100% | 2017-05-18 |  |  | update to live
QVC | garden | 2017-05-16 | 2017-05-19 | 100% | 2017-05-19 |  |  | Update to live
PVH | garden | 2017-05-16 | 2017-05-19 | 100% | 2017-05-19 |  |  | Fixing bug.
augusta | SK | 2017-05-22 | 2017-05-26 | 100% | 2017-05-10 | 5 | 0 | daily maintenance
pms | SK | 2017-05-22 | 2017-05-26 | 20% | 2017-05-10 | 5 | 0 | first version complete and wait for feedback
QVC | Garden | 2017-05-22 | 2017-05-22 | 100% | 2017-05-22 | 1 | 0 | fix layout bug
rfid-import | Garden | 2017-05-22 | 2017-05-26 | 100% | 2017-04-14 | 5 | 0 | fix minorr bugs
tribal | Kevin | 2017-05-22 | 2017-05-25 | 100% |  | 4 |  | fix the report excel table style, fix the revise team to new job information
AEO | eric | 2017-05-22 | 2017-05-22 | 100% | 2017-05-22 |  |  | UPDATE AEO GCARD
ORC | eric | 2017-05-25 | 2017-05-25 | 100% | 2017-05-25 |  |  | UPDATE STRNG
Note on I8: Richard Huang: finished and just waiting for updates
Note on I17: Please replace ‘Brand’ by ‘Division/Category’ (everywhere on site) Please add ‘Created By’ in Filter section (Main Check Order Status) Please add ‘Company Name’ in Filter and Grid (Main Check Order Status)
Note on I46: Richard Huang: james help to do this
Note on I57: Richard Huang: james help to do this
Note on I58: Richard Huang: Garden help to do this
Note on I65: Richard Huang: In the test now
Note on I68: Richard Huang: In the test Now
Note on I69: Richard Huang: In the test now
Note on I71: Richard Huang: Simon help to do it
Note on I72: Richard Huang: finished
Note on I78: Richard Huang: Simon help to do it
Note on I81: Richard Huang: finished
Note on I84: Richard Huang: Richard help to do it
Note on I233: table master_cit_style_description,master_cit_company
Note on I235: 修改order style字段、detail表master_pack_qty在CKJ&CKU&Speedo US/CANADA 为1、添加agent name、修改当订单只有一个detail但是action为cancel时，order表不保存